Graha Research Research Internship · 18-Week Gantt Project Plan Digital Product Passport Platform Implement a Digital Product Passport (DPP) platform for connected-vehicle components that captures lifecycle, material and circularity data in an interoperable, data-sovereign data-space architecture. 18 Weeks 6 Planning Clusters 1 Thesis / Collaboration Graha International GmbH · Herzogstandstr. 8 b, 85540 Haar, Germany · info@graha.de

Research Internship

Four 18-week Gantt Project Plans for thesis and research collaboration

Graha International GmbH offers four structured research internships, each delivered as an 18-week Gantt Project Plan organised into six best-practice planning clusters. This document details the internship highlighted below.

| INTERNSHIP 01 Predictive Maintenance Platform Design and prototype a predictive-maintenance platform for connected vehicles that combines multivariate time-series modelling, causal AI and explainable remaining-useful-life estimation. | INTERNSHIP 02 ESG Platform with GraphRAG Build an Environmental, Social and Governance (ESG) analytics platform that uses a Knowledge Graph and Retrieval-Augmented Generation (GraphRAG) to turn fragmented sustainability data into explainable, auditable ESG insights. | INTERNSHIP 03 Digital Product Passport Platform Implement a Digital Product Passport (DPP) platform for connected-vehicle components that captures lifecycle, material and circularity data in an interoperable, data-sovereign data-space architecture. | INTERNSHIP 04 Digital Twin Platform Develop a Digital Twin platform that mirrors onboard vehicle systems in real time, fusing sensor telemetry with physics- and data-driven models for simulation, monitoring and what-if analysis. |
| --- | --- | --- | --- |

This document, Digital Product Passport Platform

Implement a Digital Product Passport (DPP) platform for connected-vehicle components that captures lifecycle, material and circularity data in an interoperable, data-sovereign data-space architecture.

Our Research Plan

Digital Product Passport Platform  ·  18-Week Gantt Project Plan

Overview

This internship contributes to Graha International's research on data spaces and the circular economy. The intern designs and prototypes a Digital Product Passport (DPP) platform that records the lifecycle, material composition and circularity attributes of connected-vehicle components and makes them securely shareable across the value chain.

Structured as an 18-week Gantt Project Plan, the work is suitable as the practical basis for a Bachelor's or Master's thesis or a research collaboration. It emphasises interoperability, data sovereignty and alignment with emerging Digital Product Passport regulation.

Objectives

Model product-passport data: identity, materials, lifecycle events and circularity attributes.

Design an interoperable DPP data model aligned with relevant standards and regulation.

Implement secure, data-sovereign sharing of passport data across value-chain actors.

Provide passport access through a verifiable identifier and a clear user view.

Evaluate interoperability, data integrity and access control of the platform.

Candidate Profile

Studies in Computer Science, Information Systems, Industrial Engineering or a related field.

Solid programming skills; interest in APIs, data modelling and distributed systems.

Basic understanding of data spaces, identifiers and access control.

Interest in sustainability, the circular economy and regulatory-driven systems.

Independent, structured working style and good scientific-writing skills.

18-Week Gantt Project Plan

The plan is organised into six best-practice planning clusters spanning 18 weeks. Each cluster states its focus, key activities and a milestone that must be reached before the next cluster begins.

WEEKS 1-3     Cluster 1 - Onboarding & Foundations

Settle in, set up the working environment, and agree the detailed plan and success criteria with the academic and industrial supervisors.

KEY ACTIVITIES

Onboarding at Graha International: tooling, data-governance and NDA briefing.

Familiarisation with Digital Product Passport concepts, data spaces and the circular economy.

Set up a reproducible environment: version control, experiment tracking and a containerised workspace.

Refine scope, success criteria and the detailed 18-week work plan with the supervisor.

Milestone, Approved internship work plan and a running, reproducible development environment.

WEEKS 4-6     Cluster 2 - Literature Review & Requirements

Build the scientific foundation through a structured literature review and a precise requirements and evaluation specification.

KEY ACTIVITIES

Structured literature review on Digital Product Passports and circular-economy data.

Survey of DPP regulation, identifier schemes and data-space standards.

Stakeholder and requirements analysis; definition of the core use cases and KPIs.

Draft the conceptual approach and the evaluation methodology with metrics and baselines.

Milestone, Literature-review report and an agreed requirements and evaluation plan.

WEEKS 7-9     Cluster 3 - Data Engineering & System Architecture

Prepare the data assets and design the interoperable, data-sovereign architecture.

KEY ACTIVITIES

Define the DPP data model: identity, materials, lifecycle events and circularity attributes.

Map the data model to relevant interoperability standards.

Design the platform architecture: passport store, data-space connector, API and access layers.

Specify the verifiable identifier scheme and the data-sharing interfaces.

Milestone, Architecture design document and an interoperable DPP data model.

WEEKS 10-13     Cluster 4 - Implementation & Modelling

Implement the DPP platform and the secure data-sharing components.

KEY ACTIVITIES

Implement the passport store and the lifecycle-event ingestion services.

Build the data-space connector for sovereign, policy-controlled data exchange.

Implement access control and a verifiable-identifier resolution service.

Build the passport view that presents lifecycle and circularity data to users.

Milestone, Working DPP-platform prototype covering the core passport-sharing use case.

WEEKS 14-16     Cluster 5 - Evaluation, Validation & Hardening

Evaluate, validate and harden the prototype with a focus on interoperability.

KEY ACTIVITIES

Define and run experiments on interoperability, data integrity and access control.

Validate passport exchange against the agreed standards and use cases.

Assess robustness and security of the sovereign data-sharing flow.

Iterate on the data model and the connectors based on the findings.

Milestone, Evaluation report with quantitative results and a validated, hardened prototype.

WEEKS 17-18     Cluster 6 - Documentation, Thesis & Final Defence

Consolidate the documentation, draft the thesis material and present the results.

KEY ACTIVITIES

Consolidate code, documentation and reproducibility instructions.

Write the thesis-ready report covering method, results and limitations.

Prepare and deliver the final presentation and a live demo.

Hand over the platform, the data model and the backlog of future work to Graha.

Milestone, Final thesis-ready report, final presentation and a complete handover package.

Expected Outcomes

A reproducible, documented Digital Product Passport platform prototype.

An interoperable, standards-aligned DPP data model.

A data-sovereign passport-sharing component with access control.

A thesis-ready scientific report on interoperable product passports.

Project Timeline (Gantt Chart)

The 18-week plan visualised as a Gantt chart across Week 1 to Week 18.

Graha International GmbH

Herzogstandstr. 8 b

85540 Haar

Germany

Contact

E-Mail: info@graha.de