Graha Research Research Internship · 18-Week Gantt Project Plan Predictive Maintenance Platform Design and prototype a predictive-maintenance platform for connected vehicles that combines multivariate time-series modelling, causal AI and explainable remaining-useful-life estimation. 18 Weeks 6 Planning Clusters 1 Thesis / Collaboration Graha International GmbH · Herzogstandstr. 8 b, 85540 Haar, Germany · info@graha.de

Research Internship

Four 18-week Gantt Project Plans for thesis and research collaboration

Graha International GmbH offers four structured research internships, each delivered as an 18-week Gantt Project Plan organised into six best-practice planning clusters. This document details the internship highlighted below.

| INTERNSHIP 01 Predictive Maintenance Platform Design and prototype a predictive-maintenance platform for connected vehicles that combines multivariate time-series modelling, causal AI and explainable remaining-useful-life estimation. | INTERNSHIP 02 ESG Platform with GraphRAG Build an Environmental, Social and Governance (ESG) analytics platform that uses a Knowledge Graph and Retrieval-Augmented Generation (GraphRAG) to turn fragmented sustainability data into explainable, auditable ESG insights. | INTERNSHIP 03 Digital Product Passport Platform Implement a Digital Product Passport (DPP) platform for connected-vehicle components that captures lifecycle, material and circularity data in an interoperable, data-sovereign data-space architecture. | INTERNSHIP 04 Digital Twin Platform Develop a Digital Twin platform that mirrors onboard vehicle systems in real time, fusing sensor telemetry with physics- and data-driven models for simulation, monitoring and what-if analysis. |
| --- | --- | --- | --- |

This document, Predictive Maintenance Platform

Design and prototype a predictive-maintenance platform for connected vehicles that combines multivariate time-series modelling, causal AI and explainable remaining-useful-life estimation.

Our Research Plan

Predictive Maintenance Platform  ·  18-Week Gantt Project Plan

Overview

This internship contributes to Graha International's research line on advanced predictive maintenance for onboard and offboard vehicle systems. The intern designs and prototypes a Predictive Maintenance (PdM) platform that ingests vehicle telematics time-series, detects anomalies, estimates State of Health (SoH) and Remaining Useful Life (RUL), and produces explainable maintenance recommendations.

The work is structured as an 18-week Gantt Project Plan and is suitable as the practical basis for a Bachelor's or Master's thesis or a research collaboration. It bridges academic inquiry and industrial application, with emphasis on reliability, explainability and reproducibility.

Objectives

Build a reproducible pipeline for ingesting and cleaning multivariate vehicle telematics time-series.

Implement and compare anomaly-detection and RUL/SoH estimation models (statistical, ML and deep-learning).

Integrate a causal-reasoning layer that explains predicted failures rather than only forecasting them.

Deliver an explainable maintenance-recommendation component with confidence indicators.

Evaluate the platform against domain-informed ground truth and document the findings.

Candidate Profile

Studies in Computer Science, Data Science, Electrical/Mechanical Engineering or a related field.

Solid Python skills; familiarity with pandas, scikit-learn and a deep-learning framework.

Basic understanding of time-series analysis and machine-learning evaluation.

Interest in causal inference, explainable AI and connected-vehicle systems.

Independent, structured working style and good scientific-writing skills.

18-Week Gantt Project Plan

The plan is organised into six best-practice planning clusters spanning 18 weeks. Each cluster states its focus, key activities and a milestone that must be reached before the next cluster begins.

WEEKS 1-3     Cluster 1 - Onboarding & Foundations

Settle in, set up the working environment, and agree the detailed plan and success criteria with the academic and industrial supervisors.

KEY ACTIVITIES

Onboarding at Graha International: tooling, data-governance and NDA briefing.

Familiarisation with vehicle telematics, predictive-maintenance concepts and existing Graha assets.

Set up a reproducible environment: version control, experiment tracking and a containerised workspace.

Refine scope, success criteria and the detailed 18-week work plan with the supervisor.

Milestone, Approved internship work plan and a running, reproducible development environment.

WEEKS 4-6     Cluster 2 - Literature Review & Requirements

Build the scientific foundation through a structured literature review and a precise requirements and evaluation specification.

KEY ACTIVITIES

Structured literature review on RUL/SoH estimation, anomaly detection and causal AI for maintenance.

Survey of relevant time-series imputation methods and predictive-maintenance datasets.

Stakeholder and requirements analysis; definition of the core use cases and KPIs.

Draft the conceptual approach and the evaluation methodology with metrics and baselines.

Milestone, Literature-review report and an agreed requirements and evaluation plan.

WEEKS 7-9     Cluster 3 - Data Engineering & System Architecture

Prepare the data assets and design the end-to-end platform architecture.

KEY ACTIVITIES

Acquire, profile and clean the telematics time-series; handle gaps with selected imputation methods.

Engineer features and labels for anomaly, SoH and RUL tasks.

Design the platform architecture: ingestion, processing, modelling, explanation and API layers.

Specify the data model and the interfaces between components.

Milestone, Architecture design document and a prepared, documented dataset and data pipeline.

WEEKS 10-13     Cluster 4 - Implementation & Modelling

Implement the platform and the predictive and causal-reasoning models.

KEY ACTIVITIES

Implement the ingestion and processing pipeline as reproducible services.

Develop and train anomaly-detection and RUL/SoH models; compare statistical, ML and DL approaches.

Integrate a causal-reasoning layer that links predicted failures to likely root causes.

Build the explainable maintenance-recommendation component and a minimal review dashboard.

Milestone, Working PdM-platform prototype covering the core anomaly-to-recommendation use case.

WEEKS 14-16     Cluster 5 - Evaluation, Validation & Hardening

Evaluate, validate and harden the prototype against domain-informed ground truth.

KEY ACTIVITIES

Run controlled experiments; measure precision, recall, RMSE, R-squared and RUL error.

Validate causal explanations against literature- and domain-derived ground truth.

Assess robustness to missing data and noise; check reproducibility of results.

Iterate on the models and the pipeline based on the evaluation findings.

Milestone, Evaluation report with quantitative results and a validated, hardened prototype.

WEEKS 17-18     Cluster 6 - Documentation, Thesis & Final Defence

Consolidate the documentation, draft the thesis material and present the results.

KEY ACTIVITIES

Consolidate code, documentation and reproducibility instructions.

Write the thesis-ready report covering method, results and limitations.

Prepare and deliver the final presentation and a live demo.

Hand over the platform, datasets and backlog of future work to Graha.

Milestone, Final thesis-ready report, final presentation and a complete handover package.

Expected Outcomes

A reproducible, documented Predictive Maintenance platform prototype.

A comparative evaluation of anomaly-detection and RUL/SoH models.

An explainable, causal maintenance-recommendation component.

A thesis-ready scientific report and a reusable dataset and pipeline.

Project Timeline (Gantt Chart)

The 18-week plan visualised as a Gantt chart across Week 1 to Week 18.

Graha International GmbH

Herzogstandstr. 8 b

85540 Haar

Germany

Contact

E-Mail: info@graha.de